## Expediting Report
PO INFORMATION | [10 empty] | 专业工程师Discipline Eng. | 催交等级 Expediting Level | 检验等级 Inspection Level | 催交工程师Expediting Eng. | 生产进度计划提交日期 Manufacture Plan Submit Date | ITP提交日期 ITP Submit Date | 生产进度状态 Manufacture Status-Updated date====The green cell indicates that it has been completed/ | [6 empty] | 发货放行日期 Shipment Release Note Date | Remark
SN | Dis | OWNER | PO No. | Goods | Description | Tag No. | Vendor | Qty. | PO sign date | PO Delivery date | [6 empty] | 预计交货期=必填 Estimated Delivery date | 供货商图纸状态=必填 Vendor Dwg Status | 主要原材料/外购件/外协件状态=必填 Major raw material/Sub-order material/Components Status | 当前生产进度描述=必填 Production Progress Description | 目前主要问题=选填 Main problems | 建议解决措施=选填 Solutions Suggested | 预计终检时间=必填 Estimated FAT Date
I |  | Process Equipment
1 | PR | Manager 1 | BQ-TB09-PS-002-EE | Vessel | Centrifugal Pimp | 21-37TK1~4 21-37T1 21-37T2 | Vendor 1 | 6 | 2024.8.15 | 不迟于2025年3月6日 No later than Mar. 6, 2025 | 许彦达 | 2 | D | 吴秋远 |  |  | 2026-01-12 | AP=all completed | 原材料已经发货。Raw mats were already delivered from vendor. | completed |  |  | 2025.12.25-2025.12.31 2026.1.4-2026.1.7 | 2026.1.12
2 | PR | Manager 1 | BQ-TB09-PS-002-EE | Vessel | Centrifugal Pimp | TNK 56-040、TNK 56-050、TNK 56-250、TNK 56-350、TNK 01-300、TNK 01-450、PCK 16-800、TNK 16-300、TNK 16-350、PCK 16-600、PCK 16-550、TNK 16-050、TNK 16-500、TNK 16-200 | Vendor 1 | 14 | 2024.8.15 | 不迟于2025年3月6日 No later than Mar. 6, 2025 | 仝洪凯 | 2 | D | 吴秋远 |  |  |  | AP=all completed
3 | MI | Manager 1 | BQ-TB09-PS-002-EE | Vessel | Centrifugal Pimp | 21-37T1 21-37T2 TNK 16-050 | Vendor 1 | -3 | 2024.8.15 | 不迟于2025年3月6日 No later than Mar. 6, 2025 | 仝洪凯 | 2 | D | 吴秋远 |  |  |  | ——delete equipment, no drawings.
| MI | Manager 1 | BQ-TB09-PS-002-EE | Vessel | Centrifugal Pimp | TNK 16-750 | Vendor 1 | 1 | 2025.3.31 | 不迟于2025年6月31日 No later than June 31, 2025 | 仝洪凯 | 2 | D | 吴秋远 |  |  |  | AP=all completed | 有现货In stock |  |  |  | Cancelled | Cancelled
4 | MI | Manager 1 | BQ-TB09-PS-002-EE | Vessel | Centrifugal Pimp | 21-35E1A1-1~A4-1~7 21-35T1A1-1~A41~7 21-35T2A1-1~A41~7 21-35T3A1-1~A41~7 21-35T4A1-1~A41~7 21-35T5A1-1~A41~7 21-35T6A1-1~A21~7 21-35T7A1-1~A21~7 21-32V2A1-1~A4-1~7 21-32V3A1-1~A4-1~7 21-32V4A1-1~7 21-35V1A1-1~4 21-35V2A1-1~A4-1~7 21-35V3A1-1~A4-1~7 21-35V4A1-1~A4-1~7 21-35V5A1-1~A4-1~7 21-35V6A1-1~A4-1~7 21-35V7A1-1~A4-1~7 21-35V7A1-1~A4-1~7 21-35V10A1-1~A1-7 21-35V12A1-1~4 21-35T8A1-1~4 21-35V13A1-1~4 21-35E2A1-1~4 21-35V13A1-1~4 | Vendor 1 | 482 | 2024.9.2 | 不迟于合同签订后165天=2025.2.14 165 days after the PO is placed = Feb. 14, 2025 | 许彦达 | 2 | D | 吴秋远 | 2024.9.28 | 2024.9.15 | completed | completed | 原材料已全部到厂All raw materials have arrived at the factory. | completed |  |  | 2025.3.10-5.8 2025.6.20-7.15 | 2025.7.15-12.25
5 | MI | Manager 1 | LL-T9-PS-002-E-ERP | Tower | Centrifugal Pimp | TNK 16-050 | Vendor 1 | 1 | 2025.2.24 | 不迟于合同签订后165天=2025.3.5 165 days after the PO is placed=Mar. 5, 2025 | 仝洪凯 | 2 | D | 吴秋远 | 2024.9.28 | 2024.9.15 | 2026-01-10 | completed | 原材料有现货 Raw materials are in stock | completed |  |  | 2025.12.17-2025.12.24 | 2026.1.16
6 | MI | Manager 1 | LL-T9-PS-002-E-ERP | Tower | Centrifugal Pimp | SCR 13-100、SCR 13-200、SCR 13-300、SCR 13-400A/B | Vendor 1 | 5 | 2025.3.21 | 不迟于合同签订后200天=2025.3.5 200 days after the PO is placed=September. 2, 2025 | 仝洪凯 | 2 | D | 吴秋远 | 2024.9.28 | 2024.9.15 | 2026-01-10 | completed | 原材料有现货 Raw materials are in stock | completed |  |  | 2025.12.17-2025.12.24 | 2026.1.16
7 | MI | Manager 1 | LL-T9-PS-002-E-ERP | Tower | Centrifugal Pimp | SCR 18-350 SCR 17-350 SCR 13-100B SCR 13-200B | Vendor 1 | 4 | 2024.10.31 | 2026.1.30 | 仝洪凯 | 0 | D | 吴秋远 | —— | —— | 2026-01-10 | completed | 原材料有现货 Raw materials are in stock | completed |  |  | 2025.12.17-2025.12.24 | 2026.1.16
7 | PR | Manager 1 | LL-T9-PS-002-E-ERP | Tower | —— | —— | Vendor 1 | 28 | 2024.10.31 | 分批交货，首批交货不迟于2025年02月20日；最后一批不迟于2025年07月30日 Delivered in batches, with the first batched to be delivered no later than Feb. 20, 2025 and the last batch no later than Jul. 30, 2025 | 耿尧辰 | 3 | D | 吴秋远 | 2024.12.9 | 2024.12.9 | 2025-08-18 | completed | all delivered. | completed |  |  | 2025.3.3-3.5 2025.4.18-20 2025.5.22-24 | 2025.3.25-4.3 2025.5.9-5.15 2025.6.2-6.9 2025.6.10-6.11 2025.6.15-6.28 2025.7.5-7.14 8.12-8.18
8 | PR | Manager 1 | LL-T9-PS-002-E-ERP | Drying Unit | Gate Valve 2 | 17-52X001 17-52K001 17-52H001 17-52Z001 17-52S001 17-52RV001 17-52E001 17-52C001 17-52P001 17-52C002 17-52P002 17-52K002 17-52Z002 17-52P004 17-52RV002 17-52Z003 17-52Z004 17-52Z005 17-52Z006 17-52P003 17-52Z007 17-52Z012 17-52Z008 17-52Z011 17-52Z010 17-52V001 17-52RV003 17-52P005 17-52E002 17-52V004 | Vendor 1 | 127 | 2024.11.7 | 2025.3.22 | 耿尧辰 | 2 | B | 吴秋远 | 2024.12.3 | 2024.12.6 | main PO equipment：8/5-9/20；other materials&additional: 2026.4.15 | completed | all delivered. | 剩余的电伴热、仪表安装材料7月19日已发货。Remained electric heating and instrument installation materials delivered on July 19th. |  |  | 2025.5.8-16 2025.6.30-7.5 2025.7.9-7.10 | 2025.8.5-9.30 2026.1.25+4.18+5.20+6.25+7.19
9 | PR | Manager 1 | LL-T9-PS-002-E-ERP | Drying Unit | Gate Valve 2 | 21-32R1-1~7 21-32R2-1~7 21-32R3-1~7 21-32R4-1~7 | Vendor 3 | 28 | 2025.1.7 | 不迟于2025年8月31日 No later than Aug. 31, 2025 | 许彦达 | 2 | C | 吴秋远 | _ | 2025.3.6 | 2025-11-30 | completed | 已到场all arrived. | all delivered. |  |  | 2025.3.30-9.20 | 2025.4.28、2025.5.6、2025.5.8、2025.5.22-5.23、2025.6.2、2025.7.17、2025.8.10、2025.8.20、2025.8.24-27、2025.9.3、2025.9.8、2025.9.15、2025.9.25、2025.10.10、2025.11.21
| PR | Manager 1 | LL-T9-PS-002-E-ERP | Drying Unit | Gate Valve 2 | 21-31VA1~A4 21-31X7A1~A4 21-31V2A1-1~7 & A2-1~7 & A3-1~7 & A4-1~7 21-31X6A1~A4 21-32X7A1-1~7 21-32E1A1-1~7&A2-1~7&A3-1~7&A4-1~7 21-34X8A1-1~4~A2-1~4 | Vendor 3 | 28 | 2025.9.8 | 2025.11.10 | 许彦达 | 2 | C | 吴秋远 | _ | _ | 2025-12-25 | completed | 已到场all arrived. | completed |  |  | 2025.12.5-12.11 | 2025.12.25
10 | PR | Manager 1 | LL-T9-PS-002-E-ERP | Drying Unit | Gate Valve 2 | 21‑38COM1~36 21‑38DC1 21‑38FAN1 21‑38RS1 21‑38SHA1 21‑38DRY1 21‑38FAN2 21‑38FAN8 21‑38BUR1 21‑38NG1 21‑38DC2 21‑38FAN3 21‑38MX1 21‑38DIS1 21‑38CS1 21‑38RS2 21‑38COT1 21‑38COT2 21‑38F1 21‑38SCW6 21‑38V1 21‑38FIL01 21‑38FIL02 21‑38FIL03 | Vendor 3 | 36 | 2025.10.14 | 2025.11.30 | 许彦达 | 3 | C | 吴秋远 | — | 需要 | 2026-04-30 | completed | 已到场all arrived. | completed |  |  | 2026.1.15-2026.1.28 2026.4.18-4.21 | 2026.4.30
11 | PR | Manager 1 | LL-T9-PS-002-E-ERP | Drying Unit | Gate Valve 2 | HTR 31-670 HTR 36-480 HTR 55-250AB HTR 56-480 HTR 56-095 | Vendor 3 | 6 | 2024.12.25 | 不迟于2025年3月25 No later than Mar. 25, 2025 | 仝洪凯 | 2 | B | 吴秋远 | 2025.1.20 | 2025.1.14 | 2025-10-10 | completed | 原材料已全部到厂All raw materials have arrived at the factory. | all delivered. |  |  | 2025.9.15-9.18 | 2025.10.18
12 | PR | Manager 1 | LL-T9-PS-002-E-ERP | Drying Unit | Process Filter | FLT-31-570A/B FLT-51-570A/B | Vendor 3 | 4 | 2025.4.22 | 2025.6.15 | 仝洪凯 | 3 | C | 吴秋远 | _ | 2025.4.27 | 2025-08-05 | completed | 已到场all arrived. | all delivered. |  |  | 2025.7.10-13 | 2025.7.15
13 | PR | Manager 1 | LL-T9-PS-002-E-ERP | Drying Unit | Heat Exchanger | FLT31-100A/B/C/D， FLT51-100A/B/C/D | Vendor 3 | 8 | 2025.2.26 | 2025.6.30 | 仝洪凯 | 2 | C | 吴秋远 | _ | 2025.3.13 | 2025-11-30 | completed | 原材料已全部到厂All raw materials have arrived at the factory. | all delivered. |  |  | 2025.9.22-9.26 2025.11.25-11.26 | 2025.12.6
14 | PR | Manager 1 | LL-T9-PS-002-E-ERP | Drying Unit | Heat Exchanger | _ | Vendor 2 | 1 | 2025.5.19 | 2025.10.30 | 许彦达 | 2 | B | 吴秋远 |  | 需要 | / | / | / | / | / | / | / | 2025.10.30
| MI | Manager 1 | LL-T9-PS-002-E-ERP | Drying Unit | Heat Exchanger | _ | Vendor 2 | 1 | 2025.6.20 | 2025.10.30 |  |  |  | 吴秋远 |  |  | / | / | / | / | / | / | / | 2025.10.30
| LO | Manager 2 | MM-T29-PS-E-02-008 | DCP System | Heat Exchanger | 空气过滤器 Air Filter 25-45FLT40-150 鼓风机 Air Blower 25-45FAN40-160 燃气炉 Gas Furnace 25-45BUR40-170 湿料皮带输送机 Wet Material Belt Conveyor 25-45CNV40-100 混料机 Mixer 25-45MXR40-130 回转干燥机 Rotary Dryer 25-45DRY40-200 润滑油泵 Lubrication Oil Pump 25-45PUP40-200 干料螺旋输送机 Dry Material Screw Conveyor 25-45SCW40-250 干料卸料阀 Dry Material Discharge Valve 25-45RVL40-220 返料刮板输送机 Return Scraper Conveyor 25-45BUR 40-500 干燥尾气布袋除尘器 Drying Exhaust Gas Bag Filter 25-45FLT40-230 布袋除尘器卸料阀 Bag Filter Discharge Valve 25-45RVL40-230A/B/C/D 布袋除尘器刮板输送机 Bag Filter Scraper Conveyor 25-45SCW40-240 引风机 Induced Draft Fan 25-45FAN40-270A/B 烟囱 Chimney 25-45CHM40-290 产品料仓 Product Silo 25-45SIL40-500 产品缓冲仓布袋除尘器 Product Buffer Bin Bag Filter 25-45FLT40-500 产品缓冲仓布袋除尘器引风机 Product Buffer Bin Bag Filter Induced Draft Fan 25-45FAN40-500 产品斗提机 Product Bucket Elevator 25-45ELE40-260 产品返料卸料阀 Product Return Discharge Valve 25-45RVL40-500 管道除铁器 Pipeline Magnetic Separator 25-45IRN40-001 筛分机 Screening Machine 25-45Z40-001 破碎机 Crusher 25-45CRU40-100 空压机 Air Compressor 25-45COM40-001A/B 缓冲罐 Buffer Tank 25-45VEL40-001 空干机 Air Dryer 25-45DRY40-001 压缩空气过滤器 Compressed Air Filter 25-45FLT40-001/002/003 发送罐 Pressure Vessel / Conveying Tank 25-45VEL40-002A/B 产品料仓仓顶除尘器 Product Silo Top Bag Filter 25-45FLT40-004A/B/C/D 产品料仓引风机 Product Silo Induced Draft Fan 25-45FAN40-001A/B/C/D | Vendor 2 | 1 | 2026.3.2 | 回转干燥机Rotary dryer、仪表meter-7.30。 燃气炉gas stove、布袋除尘器Bag dust collector、混料机mixer、非标管道Non-standard pipeline、外购设备（风机、空压机、螺旋输送机等）和管道Outsourced equipment (fans, air compressors, screw conveyors, etc.) and pipelines-7.10 |  |  |  | 吴秋远 |  |  | 2026.8.10 | completed | 原材料已全部到厂All raw materials have arrived at the factory. | 陆续发货中,主要设备材料8月10号前发完。delivery ongoing, main equipment & materials will be delivered before 10th Aug. |  |  | 2026.6.20-25,7.15-20 | 2026.8.10
15 | MI | Manager 2 | MM-T29-PS-E-02-008 | DCP System | Heat Exchanger | FLT 56-100 FLT 36-100 | Vendor 2 | 2 | 2025.7.23 | 2025.11.15 | 仝洪凯 | 3 | C | 吴秋远 |  | 2025.7.31 | 2026/2/10 2026.3.31 | completed | 有现货In stock | all delivered. |  |  | 2026.1.6-1.22 2026.3.20-3.23 | 2026/2/10 2026.4.10
16 | MI | Manager 2 | MM-T29-PS-E-02-008 | DCP System |  | 21-30SEW01~84 21-37SEW04 25-41SEW01~10 25-42SEW01~04 25-43SEW06/07/09 25-44SEW01~06 17-52SEW01~15 02-86SEW04 02-86SEW01~03 17-51SEW01~12 21-37SEW01~03 25-41SEW11~15 25-42SEW05~06 25-43SEW01~05/08 25-44SEW07~08 17-71SEW1 21-71SEW1 | Vendor 2 | 159 | 2025.6.20 | 2025.7.20 | 耿尧辰 | 4 | D | 杨志捷 | NA | NA | 2025-08-15 | completed | arrived | completed |  |  | — | 2025.8.15
17 | MI | Manager 2 | MM-T29-PS-E-02-008 | DCP System | Belt Conveyer |  | Vendor 3 | 1 | 2025.5.23 | 2025.12.31 | 田建行 | 3 | C | 吴秋远 |  | 需要 | 石灰石破碎生产线/Limestone crushing production Line-3.20 | completed | completed | all delivered. |  |  | 2026.2.5-2.9 | 2026.3.15
| MI | Manager 2 | MM-T29-PS-E-02-008 | DCP System | Belt Conveyer |  | Vendor 3 | 1 | 2025.5.23 | 2025.12.31 | 田建行 | 3 | C | 吴秋远 |  |  | 石灰石磨粉系统/Limestone grinding system-3.30 | completed |  | completed |  |  | 2026.3.11-3.23 | 2026.5.30
| LO | Manager 2 | MM-T29-PS-E-02-008 | DCP System | Belt Conveyer |  | Vendor 3 | 1 | 2025.5.23 | 2025.12.31 | 田建行 | 3 | C | 吴秋远 |  |  | 氢氧化钙系统/Hydrated Lime system-3.30 | completed |  | completed |  |  | 2026.3.10-3.15 4.23-4.26 | 2026.5.30
| LO | Manager 2 | MM-T29-PS-E-02-008 | DCP System | Belt Conveyer |  | Vendor 3 | 1 | 2025.5.23 | 2025.12.31 | 田建行 | 3 | C | 吴秋远 |  |  | 原料输送系统/Raw material transportation system、成品系统/Finished product system3.1 | completed |  | all delivered. |  |  | 2026.1.29-1.31 | 2026.3.10
18 | LO | Manager 2 | MM-T29-PS-E-02-008 | Air Compressor |  | 02-19K01AB 02-19K01CD | Vendor 2 | 16 | 2025.7.21 | 2025.11.30 | 许彦达 | 4 | C | 阎毅 |  | 2025.7.29 | 2026-01-20 | completed 已完成 | The main raw materials have arrived at the factory.主材料已到厂 | Manufacture finished. |  |  | 2025.11.21-22；2025.12.2-3 | 2026.1.20
19 | LO | Manager 2 | MM-T29-PS-E-02-008 | Air Compressor |  | 25-PSV-41-001A/B 25-PSV-41-002A/B 25-PSV-43-001A/B 25-PSV-43-002A/B 02-PSV-86-001 25-PSV-42-001 25-PSV-44-001 | Vendor 2 | 11 | 2025.7.24 | 2025.9.30 | 耿尧辰 | 4 | C | 阎毅 |  | 2025.8.4 | 2025-11-05 | completed 已完成 | The main raw materials have arrived at the factory.主材料已到厂 | Manufacture finished. |  |  | 2025.9.20 | 2025.11.05