## PSR
[8 empty] | 0 | [7 empty] | CONTRACT PRICE: | 1000 |  | Rebaseline PLAN |  | F'CAST |  | ACTUAL | 2026-09-23 | [72 empty] | 2024-03-29 | 2024-04-26 | 2024-05-31 | 2024-06-28 | 2024-07-26 | 2024-08-30 | 2024-09-27 | 2024-10-25 | 2024-11-29 | 2024-12-27 | 2025-01-31 | 2025-02-28 | 2025-03-28 | 2025-04-25 | 2025-05-30 | 2025-06-27 | 2025-07-25 | 2025-08-29 | 2025-09-26 | 2025-10-31 | 2025-11-28 | 2025-12-26 | 2026-01-30 | 2026-02-27 | 2026-03-27 | 2026-04-24 | 2026-05-10
[15 empty] | DELTA | 0 | 0 |  | 0% | 0 | 0% | 0 | 0% | 0 | SHORT LIST ISSUED | [7 empty] | PURCHASE ORDER PLACED | [23 empty] | RECEIVED RAW MATERIAL | [11 empty] | SHIPPING [FOB OR EX-WORKS] | [17 empty] | INCOMING CONTROL ON SITE IS DONE |  |  |  | FINAL TECHNICAL DOCUMENTATION PROVIDED |  |  |  |  | Rebaseline Plan Cumulative | bar: 2024-03-29 to 2026-05-10
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 101 | 102 | 103 | 104 | 105 | 106 |  | 107 | 108 | 109 | 110 | 111 | 112 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | ETA1 | ETA2 | ETA3 | 分析 | ETA4 | INCOMING CONTROL 1 | INCOMING CONTROL 2 | INCOMING CONTROL 3 | INCOMING CONTROL 4 | [5 empty] | Rebaseline Weekly | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[19 empty] | SHORT LIST ISSUED 13: RECEIVE MR; SHORT LIST ISSUED 17: ISSUE RFQ TO BIDDER; PURCHASE ORDER PLACED 21: BIDDER RESPONSE DATE; PURCHASE ORDER PLACED 25: ISSUE TBE; PURCHASE ORDER PLACED 29: ISSUE CBE; PURCHASE ORDER PLACED 33: LOA; PURCHASE ORDER PLACED 37: PURCHASE ORDER; PURCHASE ORDER PLACED 41: ISSUED UPO TO OWNER; RECEIVED RAW MATERIAL 45: RECEIVE KEY VENDOR DATA; RECEIVED RAW MATERIAL 49: ITP; RECEIVED RAW MATERIAL 53: RAW MATERIAL DELIVERED TO VENDOR'S SHOP; SHIPPING [FOB OR EX-WORKS] 57: COMPLETE FACTORY ACCEPTANCE TEST; SHIPPING [FOB OR EX-WORKS] 61: FABRICATION PERIOD; SHIPPING [FOB OR EX-WORKS] 62: READY FOR SHIPMENT; SHIPPING [FOB OR EX-WORKS] 66: ETD; SHIPPING [FOB OR EX-WORKS] ETA1: ETA |  |  | RECEIVE ON SITE & INCOMING CONTROL | [8 empty] | Actual Cumulative | 0% | 0% | 0% | 0.08% | 0.7% | 1.27% | 3.2% | 4.5% | 6.604% | 8.5% | 10.72% | 14.01% | 16.85% | 23.86% | 31.08% | 35.92% | 44.39% | 50.67% | 56.28% | 63.36% | 68.93% | 71.22% | 76.1% | 79.41% | 81.36% | 86.89% | 88.23%
DISCIPLINE [CODE] | UNIT [CODE] | UNIT UNIQUE [CODE] | SUB UNIT [CODE] | PO [DESCRIPTION] | MR [NUMBER] | MR [DESCRIPTION] | SUPPLIER | PO No | TAG NUMBER | EQUIPMENT / MATERIAL DESCRIPTION | QTY | UOM | PERCENTAGE [%] | OVERALL WEIGHT FACTOR % | ATTACHMENT [F] PRICE [USD] | COST BREAKDOWN | TOTAL COST | PLAN CUMULATIVE [%] COMPLETE | Rebaseline PLAN CUMULATIVE [%] COMPLETE | Rebaseline PLAN CUMULATIVE EARNED WEIGHT | F'CAST CUMULATIVE [%] COMPLETE | F'CAST CUMULATIVE EARNED WEIGHT | ACTUAL CUMULATIVE [%] COMPLETE2 | ACTUAL CUMULATIVE EARNED WEIGHT3 | PLAN [MR] | Rebaseline Plan | FORECAST [MR] | ACTUAL [MR] | PLAN [RFQ] | Rebaseline Plan | FORECAST [RFQ] | ACTUAL [RFQ] | PLAN [BIDDER] | Rebaseline Plan | FORECAST [BIDDER] | ACTUAL [BIDDER] | PLAN [ISSUE TBE] | Rebaseline Plan | FORECAST [ISSUE TBE] | ACTUAL [ISSUE TBE] | PLAN [ISSUE CBE] | Rebaseline Plan | FORECAST [ISSUE CBE] | ACTUAL [ISSUE CBE] | PLAN [LOA] | Rebaseline Plan | FORECAST [LOA] | ACTUAL [LOA] | PLAN [PO] | Rebaseline Plan [PO] | FORECAST [PO] | ACTUAL [PO] | PLAN [ISSUED UPO] | Rebaseline Plan | FORECAST [ISSUED UPO] | ACTUAL [ISSUED UPO] | PLAN [RECEIVE KVD] | Rebaseline Plan | FORECAST [RECEIVE KVD] | ACTUAL [RECEIVE KVD] | PLAN [ITP] | Rebaseline Plan [ITP] | FORECAST [ITP] | ACTUAL [ITP] | PLAN [RAW MATERIAL] | Rebaseline Plan | FORECAST [RAW MATERIAL] | ACTUAL [RAW MATERIAL] | PLAN [COMPLETE FAT] | Rebaseline Plan [COMPLETE FAT] | FORECAST [COMPLETE FAT] | ACTUAL [COMPLETE FAT] | FD | PLAN [SHIPMENT] | Rebaseline Plan | FORECAST [SHIPMENT] | ACTUAL [SHIPMENT] | PLAN [ETD] | Rebaseline Plan [ETD] | FORECAST [ETD] | ACTUAL [ETD] | PLAN [ETA] | Rebaseline Plan [ETA] | FORECAST [ETA] |  | ACTUAL [ETA] | PLAN [RECEIVE ON SITE] | Rebaseline Plan [RECEIVE ON SITE] | FORECAST [RECEIVE ON SITE] | ACTUAL [RECEIVE ON SITE] | PLAN [FIN/AL TECHNICAL DOCUMENTATION] | Rebaseline Plan [FIN/AL TECHNICAL DOCUMENTATION] | FORECAST [FIN/AL TECHNICAL DOCUMENTATION] | ACTUAL [FIN/AL TECHNICAL DOCUMENTATION] | 列74 | Actual Weekly | 0% | 0% | 0% | 0.08% | 0.62% | 0.57% | 1.93% | 1.3% | 2.104% | 1.896% | 2.22% | 3.29% | 2.84% | 7.01% | 7.22% | 4.84% | 8.47% | 6.28% | 5.61% | 7.081% | 5.566% | 2.292% | 4.88% | 3.31% | 1.953% | 5.527% | 1.34%
PR | 7-30 | 21-30 | 00 | Purchase order 01 | PRO-7-30-001-PEP-SI | K2S-反应器（曼海姆炉t硫酸钾处理单元 | Supplier 1 | BP-T24B09-PS-E-02-003 | 21-32R1-1~7 21-32R2-1~7 21-32R3-1~7 21-32R4-1~7 | Storage Tank | 112 |  | 1% | 1% | 1 | 1 | 1 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 2024-06-30 | 2024-04-25 | 2024-04-25 | 2024-04-25 | 2024-07-07 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-08-11 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-08-25 | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-08-28 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-09-10 | 2024-12-23 | 2024-12-23 | 2024-12-23 | 2024-09-20 | 2025-01-07 | 2025-01-07 | 2025-01-07 | 2024-09-23 | 2025-01-08 | 2025-01-08 | 2025-01-08 | 2024-10-05 | 2025-01-23 | 2025-01-23 | 2025-01-23 | 2024-10-11 | 2025-02-28 | 2025-02-28 | 2025-03-07 | 2025-01-18 | 2025-03-14 | 2025-03-14 | 2025-03-14 | 2025-08-06 | 2025-04-21 | 2025-04-21 | 2025-03-20 | 330 | 2025-08-16 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-08-31 | 2025-04-10 | 2025-04-10 | 2025-04-10 | 2025-09-27 | 2025-05-03 | 2025-05-03 | 116 | 2025-05-03 | 2025-09-30 | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2026-07-27 | 2026-01-24 | 2026-07-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MI | 21-3 | 21-30 | -3 | Purchase order 01 | MIG-21-30-32-002 | K2S-反应器（曼海姆炉t硫酸钾处理单元 | Supplier 1 | BS-PS-E-02-01 | 21-31VA1~A4 21-31X7A1~A4 21-31V2A1-1~7 & A2-1~7 & A3-1~7 & A4-1~7 21-31X6A1~A4 21-32X7A1-1~7 21-32E1A1-1~7&A2-1~7&A3-1~7&A4-1~7 21-34X8A1-1~4~A2-1~4 | Storage Tank | 32 |  | 1% | 1% | 1 | 1 | 1 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 2024-06-30 | 2024-04-25 | 2024-04-25 | 2024-04-25 | 2024-07-07 | 2024-04-26 | 2024-04-26 | 2024-04-26 | 2024-08-11 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-08-25 | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-08-28 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-09-10 | 2024-12-23 | 2024-12-23 | 2024-12-23 | 2024-09-20 | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2024-09-23 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2024-10-05 | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2024-10-11 | 2025-12-01 | 2025-12-01 | NA | 2025-01-18 | 2025-11-15 | 2025-11-15 | 2025-11-15 | 2025-08-06 | 2025-12-09 | 2025-12-11 | 2025-12-11 | 330 | 2025-08-16 | 2025-12-14 | 2025-12-25 | 2025-12-25 | 2025-08-31 | 2025-12-29 | 2026-01-09 | 2026-01-09 | 2025-09-27 | 2026-01-13 | 2026-01-23 | 137 | 2026-01-23 | 2025-09-30 | 2026-03-24 | 2026-04-03 | 2026-04-03 | 2026-07-27 | 2026-05-23 | 2026-07-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MI | 21-3 | 21-30 | -3 | Purchase order 02 | MIG-21-30-32-002 | Pump Station | Supplier 2 | BP-T2-PTT - 001 | 21-32V2A1-1~A4-1 21-32V2A1-2~A4-2 21-32V2A1-3~A4-3 21-32V2A1-4~A4-4 21-32V2A1-5~A4-5 21-32V2A1-6~A4-6 21-32V2A1-7~A4-7 | Storage Tank | 28 |  | 1% | 1% | 1 | 1 | 1 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-27 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-08-01 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-09-05 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-09-08 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-09-19 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-10-09 | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-10-12 | 2024-09-05 | 2024-09-05 | 2024-09-05 | 2024-10-24 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-08 | 2024-11-01 | 2024-11-01 | 2024-11-01 | 2025-04-27 | 2025-07-05 | 2025-07-05 | 2025-07-05 | 210 | 2025-05-07 | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-05-22 | 2025-08-09 | 2025-08-09 | 2025-08-09 | 2025-06-18 | 2025-09-28 | 2025-09-28 | 391 | 2025-09-28 | 2025-06-21 | 2025-12-30 | 2026-01-30 | 2026-01-30 | 2025-12-18 | 2026-02-28 | 2025-11-14 | 2025-11-14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR | 7-30 | 21-30 | 00 | Purchase order 02 | PRO-7-30-001-PEP-SI | Heat Exchanger Unit | Supplier 3 | BP-T2-PTT - 001 | 21-32V3A1-1~A4-1 21-32V3A1-2~A4-2 21-32V3A1-3~A4-3 21-32V3A1-4~A4-4 21-32V3A1-5~A4-5 21-32V3A1-6~A4-6 21-32V3A1-7~A4-7 | Storage Tank | 28 |  | 1% | 1% | 1 | 1 | 1 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-27 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-08-01 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-09-05 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-09-08 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-09-19 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-10-09 | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-10-12 | 2024-09-05 | 2024-09-05 | 2024-09-05 | 2024-10-24 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-08 | 2024-11-01 | 2024-11-01 | 2024-11-01 | 2025-04-27 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 210 | 2025-05-07 | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-05-22 | 2025-08-09 | 2025-08-09 | 2025-08-09 | 2025-06-18 | 2025-09-28 | 2025-09-28 | 391 | 2025-09-28 | 2025-06-21 | 2025-12-30 | 2026-01-30 | 2026-01-30 | 2025-12-18 | 2026-02-28 | 2025-11-14 | 2025-11-14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR | 7-30 | 21-30 | 00 | Purchase order 02 | PRO-7-30-001-PEP-SI | Heat Exchanger Unit | Supplier 2 | BP-T2-PTT - 001 | 21-32V4A1-1 21-32V4A1-2 21-32V4A1-3 21-32V4A1-4 21-32V4A1-5 21-32V4A1-6 21-32V4A1-7 | Storage Tank | 7 |  | 1% | 1% | 1 | 1 | 1 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-27 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-08-01 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-09-05 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-09-08 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-09-19 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-10-09 | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-10-12 | 2024-09-05 | 2024-09-05 | 2024-09-05 | 2024-10-24 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-08 | 2024-11-01 | 2024-11-01 | 2024-11-01 | 2025-04-27 | 2025-06-20 | 2025-06-20 | 2025-06-20 | 210 | 2025-05-07 | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-05-22 | 2025-08-09 | 2025-08-09 | 2025-08-09 | 2025-06-18 | 2025-09-30 | 2025-09-30 | 393 | 2025-09-30 | 2025-06-21 | 2025-12-30 | 2026-01-30 | 2026-01-30 | 2025-12-18 | 2026-02-28 | 2025-11-14 | 2025-11-14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR | 7-30 | 21-30 | 00 | Purchase order 02 | PRO-7-30-001-PEP-SI | Heat Exchanger Unit | Supplier 1 | BS-PS-E-02-01 | 21-35T1A1-1~A4-1 21-35T1A1-2~A4-2 21-35T1A1-3~A4-3 21-35T1A1-4~A4-4 21-35T1A1-5~A4-5 21-35T1A1-6~A4-6 21-35T1A1-7~A4-7 | Storage Tank | 28 |  | 1% | 1% | 1 | 1 | 1 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-27 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-08-01 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-09-05 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-09-08 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-09-19 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-10-09 | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-10-12 | 2024-09-05 | 2024-09-05 | 2024-09-05 | 2024-10-24 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-08 | 2024-11-01 | 2024-11-01 | 2024-11-01 | 2025-04-27 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 210 | 2025-05-07 | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2025-05-22 | 2025-07-25 | 2025-07-25 | 2025-07-25 | 2025-06-18 | 2025-09-30 | 2025-09-30 | 393 | 2025-09-30 | 2025-06-21 | 2025-12-30 | 2026-01-30 | 2026-01-30 | 2025-12-18 | 2026-02-28 | 2025-11-14 | 2025-11-14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR | 7-30 | 21-30 | 00 | Purchase order 02 | PRO-7-30-001-PEP-SI | Heat Exchanger Unit | Supplier 3 | BS-PS-E-02-01 | 21-35T6A1-1~A2-1 21-35T6A1-2~A2-2 21-35T6A1-3~A2-3 21-35T6A1-4~A2-4 21-35T6A1-5~A2-5 21-35T6A1-6~A2-6 21-35T6A1-7~A2-7 | Centrifugal Pump | 14 |  | 1% | 1% | 1 | 1 | 1 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-27 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-08-01 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-09-05 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-09-08 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-09-19 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-10-09 | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-10-12 | 2024-09-05 | 2024-09-05 | 2024-09-05 | 2024-10-24 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-08 | 2024-11-01 | 2024-11-01 | 2024-11-01 | 2025-04-27 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 210 | 2025-05-07 | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-05-22 | 2025-08-09 | 2025-08-09 | 2025-08-09 | 2025-06-18 | 2025-09-27 | 2025-09-27 | 390 | 2025-09-27 | 2025-06-21 | 2025-12-30 | 2026-01-30 | 2026-01-30 | 2025-12-18 | 2026-02-28 | 2025-11-14 | 2025-11-14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR | 7-30 | 21-30 | 00 | Purchase order 02 | PRO-7-30-001-PEP-SI | Pump Station | Supplier 2 | BS-PS-E-02-01 | 21-35T7A1-1~A2.-1 21-35T7A1-2~A2-2 21-35T7A1-3~A2-3 21-35T7A1-4~A2-4 21-35T7A1-5~A2-5 21-35T7A1-6~A2-6 21-35T7A1-7~A2-7 | Heat Exchanger | 14 |  | 1% | 1% | 1 | 1 | 1 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-27 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-08-01 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-09-05 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-09-08 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-09-19 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-10-09 | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-10-12 | 2024-09-05 | 2024-09-05 | 2024-09-05 | 2024-10-24 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-08 | 2024-11-01 | 2024-11-01 | 2024-11-01 | 2025-04-27 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 210 | 2025-05-07 | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2025-05-22 | 2025-07-25 | 2025-07-25 | 2025-07-25 | 2025-06-18 | 2025-10-15 | 2025-10-15 | 408 | 2025-10-15 | 2025-06-21 | 2025-12-24 | 2026-01-30 | 2026-01-30 | 2025-12-18 | 2026-02-22 | 2025-11-14 | 2025-11-14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR | 7-30 | 21-30 | 00 | Purchase order 02 | PRO-7-30-001-PEP-SI | Pump Station | Supplier 2 | BS-PS-E-02-01 | 21-35V1A1-1 21-35V1A1-2 21-35V1A1-3 21-35V1A1-4 | Centrifugal Pump | 4 |  | 1% | 1% | 1 | 1 | 1 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-27 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-08-01 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-09-05 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-09-08 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-09-19 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-10-09 | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-10-12 | 2024-09-05 | 2024-09-05 | 2024-09-05 | 2024-10-24 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-08 | 2024-11-01 | 2024-11-01 | 2024-11-01 | 2025-04-27 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 210 | 2025-05-07 | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-05-22 | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-06-18 | 2025-09-30 | 2025-09-30 | 393 | 2025-09-30 | 2025-06-21 | 2025-12-30 | 2026-01-30 | 2026-01-30 | 2025-12-18 | 2026-02-28 | 2025-11-14 | 2025-11-14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR | 7-30 | 21-30 | 00 | Purchase order 02 | PRO-7-30-001-PEP-SI | Pump Station | Supplier 2 | BS-PS-E-02-01 | 21-35V2A1-1~A4-1 21-35V2A1-2~A4-2 21-35V2A1-3~A4-3 21-35V2A1-4~A4-4 21-35V2A1-5~A4-5 21-35V2A1-6~A4-6 21-35V2A1-7~A4-7 | Heat Exchanger | 28 |  | 1% | 1% | 1 | 1 | 1 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-27 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-08-01 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-09-05 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-09-08 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-09-19 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-10-09 | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-10-12 | 2024-09-05 | 2024-09-05 | 2024-09-05 | 2024-10-24 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-08 | 2024-11-01 | 2024-11-01 | 2024-11-01 | 2025-04-27 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 210 | 2025-05-07 | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-05-22 | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-06-18 | 2025-09-30 | 2025-09-30 | 393 | 2025-09-30 | 2025-06-21 | 2025-12-30 | 2026-01-30 | 2026-01-30 | 2025-12-18 | 2026-02-28 | 2025-11-14 | 2025-11-14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR | 7-30 | 21-30 | 00 | Purchase order 03 | PRO-7-30-001-PEP-SI | Pump Station | Supplier 2 | BS-PS-E-02-01 | 21-35V3A1-1~A4-1 21-35V3A1-2~A4-2 21-35V3A1-3~A4-3 21-35V3A1-4~A4-4 21-35V3A1-5~A4-5 21-35V3A1-6~A4-6 21-35V3A1-7~A4-7 | Centrifugal Pump | 28 |  | 1% | 1% | 1 | 1 | 1 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-27 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-08-01 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-09-05 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-09-08 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-09-19 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-10-09 | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-10-12 | 2024-09-05 | 2024-09-05 | 2024-09-05 | 2024-10-24 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-08 | 2024-11-01 | 2024-11-01 | 2024-11-01 | 2025-04-27 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 210 | 2025-05-07 | 2025-08-05 | 2025-08-05 | 2025-08-05 | 2025-05-22 | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-06-18 | 2025-10-12 | 2025-10-12 | 405 | 2025-10-12 | 2025-06-21 | 2025-12-21 | 2026-01-30 | 2026-01-30 | 2025-12-18 | 2026-02-19 | 2025-11-14 | 2025-11-14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PR | 7-30 | 21-30 | 00 | Purchase order 04 | PRO-7-30-001-PEP-SI | Pump Station | Supplier 2 | B09-PKEL-011-E | 21-35V4A1-1~A4-1 21-35V4A1-2~A4-2 21-35V4A1-3~A4-3 21-35V4A1-4~A4-4 21-35V4A1-5~A4-5 21-35V4A1-6~A4-6 21-35V4A1-7~A4-7 | Heat Exchanger | 28 |  | 1% | 1% | 1 | 1 | 1 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-27 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-08-01 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-09-05 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-09-08 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-09-19 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-10-09 | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-10-12 | 2024-09-05 | 2024-09-05 | 2024-09-05 | 2024-10-24 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-08 | 2024-11-01 | 2024-11-01 | 2024-11-01 | 2025-04-27 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 210 | 2025-05-07 | 2025-08-05 | 2025-08-05 | 2025-08-05 | 2025-05-22 | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-06-18 | 2025-10-12 | 2025-10-12 | 405 | 2025-10-12 | 2025-06-21 | 2025-12-21 | 2026-01-30 | 2026-01-30 | 2025-12-18 | 2026-02-19 | 2025-11-14 | 2025-11-14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MI | 21-3 | 22-77 | -3 | Purchase order 04 | MIG-21-30-32-002 | Heat Exchanger Unit | Supplier 3 | BS-PS-E-02-01 | 21-35V5A1-1~A4-1 21-35V5A1-2~A4-2 21-35V5A1-3~A4-3 21-35V5A1-4~A4-4 21-35V5A1-5~A4-5 21-35V5A1-6~A4-6 21-35V5A1-7~A4-7 | Heat Exchanger | 28 |  | 1% | 1% | 1 | 1 | 1 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-27 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-08-01 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-09-05 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-09-08 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-09-19 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-10-09 | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-10-12 | 2024-09-05 | 2024-09-05 | 2024-09-05 | 2024-10-24 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-08 | 2024-11-01 | 2024-11-01 | 2024-11-01 | 2025-04-27 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 210 | 2025-05-07 | 2025-08-05 | 2025-08-05 | 2025-08-05 | 2025-05-22 | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-06-18 | 2025-10-12 | 2025-10-12 | 405 | 2025-10-12 | 2025-06-21 | 2025-12-21 | 2026-01-30 | 2026-01-30 | 2025-12-18 | 2026-02-19 | 2025-11-14 | 2025-11-14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MI | 21-3 | 22-77 | -3 | Purchase order 04 | MIG-21-30-32-002 | Heat Exchanger Unit | Supplier 3 | BS-PS-E-02-01 | 21-35V6A1-1~A4-1 21-35V6A1-2~A4-2 21-35V6A1-3~A4-3 21-35V6A1-4~A4-4 21-35V6A1-5~A4-5 21-35V6A1-6~A4-6 21-35V6A1-7~A4-7 | Gate Valve 2 | 28 |  | 1% | 1% | 1 | 1 | 1 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-27 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-08-01 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-09-05 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-09-08 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-09-19 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-10-09 | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-10-12 | 2024-09-05 | 2024-09-05 | 2024-09-05 | 2024-10-24 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-08 | 2024-11-01 | 2024-11-01 | 2024-11-01 | 2025-04-27 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 210 | 2025-05-07 | 2025-08-05 | 2025-08-05 | 2025-08-05 | 2025-05-22 | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-06-18 | 2025-10-12 | 2025-10-12 | 405 | 2025-10-12 | 2025-06-21 | 2025-12-21 | 2026-01-30 | 2026-01-30 | 2025-12-18 | 2026-02-19 | 2025-11-14 | 2025-11-14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MI | 21-3 | 22-77 | -3 | Purchase order 04 | MIG-21-30-32-002 | Heat Exchanger Unit | Supplier 3 | BS-PS-E-02-01 | 21-35V7A1-1~A4-1 21-35V7A1-2~A4-2 21-35V7A1-3~A4-3 21-35V7A1-4~A4-4 21-35V7A1-5~A4-5 21-35V7A1-6~A4-6 21-35V7A1-7~A4-7 | Gate Valve 2 | 28 |  | 1% | 1% | 1 | 1 | 1 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-27 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-08-01 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-09-05 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-09-08 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-09-19 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-10-09 | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-10-12 | 2024-09-05 | 2024-09-05 | 2024-09-05 | 2024-10-24 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-08 | 2024-11-01 | 2024-11-01 | 2024-11-01 | 2025-04-27 | 2025-07-05 | 2025-07-05 | 2025-07-05 | 210 | 2025-05-07 | 2025-08-05 | 2025-08-05 | 2025-08-05 | 2025-05-22 | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-06-18 | 2025-09-30 | 2025-09-30 | 393 | 2025-09-30 | 2025-06-21 | 2025-12-30 | 2026-01-30 | 2026-01-30 | 2025-12-18 | 2026-02-28 | 2025-11-14 | 2025-11-14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MI | 21-3 | 22-77 | -3 | Purchase order 03 | MIG-21-30-32-002 | Pump Station | Supplier 2 | B09-PKEL-011-E | 21-35V8A1-1~A4-1 21-35V8A1-2~A4-2 21-35V8A1-3~A4-3 21-35V8A1-4~A4-4 21-35V8A1-5~A4-5 21-35V8A1-6~A4-6 21-35V8A1-7~A4-7 | Gate Valve 2 | 28 |  | 1% | 1% | 1 | 1 | 1 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-27 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-08-01 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-09-05 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-09-08 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-09-19 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-10-09 | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-10-12 | 2024-09-05 | 2024-09-05 | 2024-09-05 | 2024-10-24 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-08 | 2024-11-01 | 2024-11-01 | 2024-11-01 | 2025-04-27 | 2025-05-09 | 2025-05-09 | 2025-05-09 | 210 | 2025-05-07 | 2025-08-05 | 2025-08-05 | 2025-08-05 | 2025-05-22 | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-06-18 | 2025-10-15 | 2025-10-15 | 408 | 2025-10-15 | 2025-06-21 | 2025-12-24 | 2026-01-30 | 2026-01-30 | 2025-12-18 | 2026-02-22 | 2025-11-14 | 2025-11-14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MI | 21-3 | 22-77 | -3 | Purchase order 03 | MIG-21-30-32-002 | Pump Station | Supplier 2 | B09-PKEL-011-E | 21-35V10A1-1~A1-7 | Pressure Transmitter | 7 |  | 1% | 1% | 1 | 1 | 1 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-27 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-08-01 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-09-05 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-09-08 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-09-19 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-10-09 | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-10-12 | 2024-09-05 | 2024-09-05 | 2024-09-05 | 2024-10-24 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-08 | 2024-11-01 | 2024-11-01 | 2024-11-01 | 2025-04-27 | 2025-07-05 | 2025-07-05 | 2025-07-05 | 210 | 2025-05-07 | 2025-08-05 | 2025-08-05 | 2025-08-05 | 2025-05-22 | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-06-18 | 2025-10-15 | 2025-10-15 | 408 | 2025-10-15 | 2025-06-21 | 2025-12-24 | 2026-01-30 | 2026-01-30 | 2025-12-18 | 2026-02-22 | 2025-11-14 | 2025-11-14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MI | 21-3 | 22-77 | -3 | Purchase order 03 | MIG-21-30-32-002 | Pump Station | Supplier 2 | B09-PKEL-011-E | 21-35V13A1-1~4 | Pressure Transmitter | 4 |  | 1% | 1% | 1 | 1 | 1 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-27 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-08-01 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-09-05 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-09-08 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-09-19 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-10-09 | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-10-12 | 2024-09-05 | 2024-09-05 | 2024-09-05 | 2024-10-24 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-08 | 2024-11-01 | 2024-11-01 | 2024-11-01 | 2025-04-27 | 2025-07-05 | 2025-07-05 | 2025-07-05 | 210 | 2025-05-07 | 2025-08-05 | 2025-08-05 | 2025-08-05 | 2025-05-22 | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-06-18 | 2025-10-15 | 2025-10-15 | 408 | 2025-10-15 | 2025-06-21 | 2025-12-24 | 2026-01-30 | 2026-01-30 | 2025-12-18 | 2026-02-22 | 2025-11-14 | 2025-11-14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MI | 21-3 | 22-77 | -3 | Purchase order 03 | MIG-21-30-32-002 | Pump Station | Supplier 3 | B09-PKEL-011-E | 21-35V14 A1-4 | Pressure Transmitter | 4 |  | 1% | 1% | 1 | 1 | 1 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-27 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-08-01 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-09-05 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-09-08 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-09-19 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-10-09 | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-10-12 | 2024-09-05 | 2024-09-05 | 2024-09-05 | 2024-10-24 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-08 | 2024-11-01 | 2024-11-01 | 2024-11-01 | 2025-04-27 | 2025-07-05 | 2025-07-05 | 2025-07-05 | 210 | 2025-05-07 | 2025-08-05 | 2025-08-05 | 2025-08-05 | 2025-05-22 | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-06-18 | 2025-10-15 | 2025-10-15 | 408 | 2025-10-15 | 2025-06-21 | 2025-12-24 | 2026-01-30 | 2026-01-30 | 2025-12-18 | 2026-02-22 | 2025-11-14 | 2025-11-14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MI | 21-3 | 22-77 | -3 | Purchase order 04 | MIG-21-30-32-002 | Pump Station | Supplier 2 | B09-PKEL-011-E | 21-35E2A1-1~4 | Pressure Transmitter | 4 |  | 1% | 1% | 1 | 1 | 1 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-27 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-08-01 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-09-05 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-09-08 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-09-19 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-10-09 | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-10-12 | 2024-09-05 | 2024-09-05 | 2024-09-05 | 2024-10-24 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-08 | 2024-11-01 | 2024-11-01 | 2024-11-01 | 2025-04-27 | 2025-07-05 | 2025-07-05 | 2025-07-05 | 210 | 2025-05-07 | 2025-08-05 | 2025-08-05 | 2025-08-05 | 2025-05-22 | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-06-18 | 2025-10-15 | 2025-10-15 | 408 | 2025-10-15 | 2025-06-21 | 2025-12-24 | 2026-01-30 | 2026-01-30 | 2025-12-18 | 2026-02-22 | 2025-11-14 | 2025-11-14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LS | 7G-3 | 22-77 | -3 | Purchase order 04 | LSO-7G-30-32-003-QER | Pump Station | Supplier 1 | B09-PKEL-011-E | 21-35T8A1-1~4 | Pressure Transmitter | 4 |  | 1% | 1% | 1 | 1 | 1 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-27 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-08-01 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-09-05 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-09-08 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-09-19 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-10-09 | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-10-12 | 2024-09-05 | 2024-09-05 | 2024-09-05 | 2024-10-24 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-08 | 2024-11-01 | 2024-11-01 | 2024-11-01 | 2025-04-27 | 2025-07-05 | 2025-07-05 | 2025-07-05 | 210 | 2025-05-07 | 2025-08-05 | 2025-08-05 | 2025-08-05 | 2025-05-22 | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2025-06-18 | 2025-10-15 | 2025-10-15 | 408 | 2025-10-15 | 2025-06-21 | 2025-12-24 | 2026-01-30 | 2026-01-30 | 2025-12-18 | 2026-02-22 | 2025-11-14 | 2025-11-14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LS | 7G-3 | 22-77 | -3 | Purchase order 04 | LSO-7G-30-32-003-QER | Heat Exchanger Unit | Supplier 3 | B09-PKEL-011-E | SCR 13-100 | Pressure Transmitter | 1 |  | 1% | 1% | 1 | 1 | 1 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-27 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-08-01 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-09-05 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-09-08 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-09-19 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-10-09 | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2024-10-12 | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2024-10-24 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-08 | 2024-11-01 | 2024-11-01 | 2024-11-01 | 2025-04-27 | 2025-12-22 | 2025-12-24 | 2025-12-24 | 210 | 2025-05-07 | 2025-12-27 | 2026-01-15 | 2026-01-15 | 2025-05-22 | 2026-01-06 | 2026-01-25 | 2026-01-25 | 2025-06-18 | 2026-01-21 | 2026-02-10 | 326 | 2026-02-10 | 2025-06-21 | 2026-04-01 | 2026-04-21 | 2026-04-21 | 2025-12-18 | 2026-05-31 | 2025-11-14 | 2025-11-14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LS | 7G-3 | 22-77 | -3 | Purchase order 04 | LSO-7G-30-32-003-QER | Heat Exchanger Unit | Supplier 1 | BP-T2-PTT - 001 | SCR 13-200 | Pressure Transmitter | 1 |  | 1% | 1% | 1 | 1 | 1 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-27 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-08-01 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-09-05 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-09-08 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-09-19 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-10-09 | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2024-10-12 | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2024-10-24 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-08 | 2024-11-01 | 2024-11-01 | 2024-11-01 | 2025-04-27 | 2025-12-22 | 2025-12-24 | 2025-12-24 | 210 | 2025-05-07 | 2025-12-27 | 2026-01-15 | 2026-01-15 | 2025-05-22 | 2026-01-06 | 2026-01-25 | 2026-01-25 | 2025-06-18 | 2026-01-21 | 2026-02-10 | 326 | 2026-02-10 | 2025-06-21 | 2026-04-01 | 2026-04-21 | 2026-04-21 | 2025-12-18 | 2026-05-31 | 2025-11-14 | 2025-11-14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LS | 7G-3 | 22-77 | -3 | Purchase order 04 | LSO-7G-30-32-003-QER | Heat Exchanger Unit | Supplier 2 | BP-T2-PTT - 001 | SCR 13-300 | Pressure Transmitter | 1 |  | 1% | 1% | 1 | 1 | 1 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-27 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-08-01 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-09-05 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-09-08 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-09-19 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-10-09 | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2024-10-12 | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2024-10-24 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-08 | 2024-11-01 | 2024-11-01 | 2024-11-01 | 2025-04-27 | 2025-12-22 | 2025-12-24 | 2025-12-24 | 210 | 2025-05-07 | 2025-12-27 | 2026-01-15 | 2026-01-15 | 2025-05-22 | 2026-01-06 | 2026-01-25 | 2026-01-25 | 2025-06-18 | 2026-01-21 | 2026-02-10 | 326 | 2026-02-10 | 2025-06-21 | 2026-04-01 | 2026-04-21 | 2026-04-21 | 2025-12-18 | 2026-05-31 | 2025-11-14 | 2025-11-14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LS | 7G-3 | 22-77 | -3 | Purchase order 04 | LSO-7G-30-32-003-QER | Pump Station | Supplier 2 | BP-T2-PTT - 001 | SCR 13-400AB | Pressure Transmitter | 2 |  | 1% | 1% | 1 | 1 | 1 | 0% | 0% | 0 | 0% | 0 | 0% | 0 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-27 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-08-01 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-09-05 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-09-08 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-09-19 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-10-09 | 2025-03-21 | 2025-03-21 | 2025-03-21 | 2024-10-12 | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2024-10-24 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-08 | 2024-11-01 | 2024-11-01 | 2024-11-01 | 2025-04-27 | 2025-12-22 | 2025-12-24 | 2025-12-24 | 210 | 2025-05-07 | 2025-12-27 | 2026-01-15 | 2026-01-15 | 2025-05-22 | 2026-01-06 | 2026-01-25 | 2026-01-25 | 2025-06-18 | 2026-01-21 | 2026-02-10 | 326 | 2026-02-10 | 2025-06-21 | 2026-04-01 | 2026-04-21 | 2026-04-21 | 2025-12-18 | 2026-05-31 | 2025-11-14 | 2025-11-14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0%
0%
0%
0%